## Sheet1
Item ID | Feature/User Story | Priority | Status | Estimated Effort (Points) | Assignee | Notes
PB-001 | As an Admin, I can manage user accounts (CRUD) | High | To Do | 8 | Team Lead | Includes Doctor and Patient user linking
PB-002 | As a Patient, I can register for an account | High | To Do | 5 | Backend Dev | Requires unique username validation
PB-003 | As a User, I can log in and out of the system | High | In Progress | 3 | Backend Dev | Implement session/cookie authentication
PB-004 | As a Patient, I can view my profile and medical history | Medium | To Do | 5 | Frontend Dev | Read-only view initially
PB-005 | As a Doctor, I can view my schedule and appointments | High | To Do | 8 | Fullstack Dev | Date filter for daily schedule
PB-006 | As a Patient, I can book an appointment with a doctor | High | To Do | 13 | Fullstack Dev | Doctor availability check, time slots
PB-007 | As a Doctor, I can view my list of patients | Medium | To Do | 5 | Backend Dev | Filter by gender, search by name
PB-008 | As an Admin, I can manage doctor profiles (CRUD) | High | To Do | 8 | Team Lead | Link to user accounts
PB-009 | As a User, I can change my password | Medium | To Do | 5 | Backend Dev | Secure password update
PB-010 | As a Patient, I can view and pay my bills online | Medium | To Do | 8 | Fullstack Dev | Basic bill display and status update
PB-011 | As a Doctor, I can add/update patient files | Low | Backlog | 13 |  | For medical records, diagnoses, etc.
PB-012 | As a User, I receive system notifications | Low | Backlog | 5 | Frontend Dev | Basic in-app notification display
PB-013 | As an Admin, I can generate basic reports | Low | Backlog | 8 | Data Analyst | E.g., number of appointments, patient growth
PB-014 | Implement comprehensive input validation | High | In Progress | 3 | All Developers | Client-side and server-side
PB-015 | Implement robust error handling and logging | Medium | To Do | 5 | Backend Dev | Centralized error logging